## Plan
ARC-AGI-2 — One-Month Plan (Jun 1–30, 2026)
Two-person team · A = method/model · B = infra/eval · Both = shared. Status dropdown on each row. Gate rows are the weekly go/no-go.
Week | Days | Task | Owner | Type | Status | Notes
Week 1 | Jun 1–7 | Stand up shared repo + results log on day one (don't defer) | Both | Setup | Not started
Week 1 | Jun 1–7 | Solve training tasks by hand ~1 hr/day to build puzzle intuition | Both | Study | Not started
Week 1 | Jun 1–7 | Load ARC-AGI-2 public training + eval data locally on the Mac | B | Setup | Not started
Week 1 | Jun 1–7 | Pick ONE simplest credible baseline to fork (TTT starter or TRM) | Both | Setup | Not started
Week 1 | Jun 1–7 | Get baseline running in a Kaggle GPU notebook; reproduce its public-eval score | A | Method | Not started
Week 1 | Jun 1–7 | Build local eval harness on Mac: load tasks, run solver, score with official 2-attempt metric, per-task report | B | Infra | Not started
GATE 1 | Jun 7 | Baseline reproduced on Kaggle within tolerance AND local harness matches the numbers. Can't reproduce in a week = early infra red flag. | Both | Gate
Week 2 | Jun 8–14 | Push full end-to-end baseline submission to the leaderboard | A | Method | Not started
Week 2 | Jun 8–14 | Confirm it runs inside 12h / single-GPU / no-internet envelope | A | Infra | Not started
Week 2 | Jun 8–14 | Build augmentation pipeline: rotations, reflections, color permutations | B | Infra | Not started
Week 2 | Jun 8–14 | Build candidate-generation + voting/selection scaffold | B | Infra | Not started
Week 2 | Jun 8–14 | Error analysis: cluster where the baseline fails by task type | Both | Study | Not started
GATE 2 | Jun 14 | Scored leaderboard submission landed, comfortably inside compute budget, with a ranked list of failure clusters to attack. | Both | Gate
Week 3 | Jun 15–21 | Pick 2–3 high-leverage improvements from error analysis (no more) | Both | Method | Not started
Week 3 | Jun 15–21 | Push the training/model side: LoRA rank, augmentation count, inference-time compute | A | Method | Not started
Week 3 | Jun 15–21 | Own the two-attempt strategy: make the 2nd guess diverse, not a near-duplicate | B | Infra | Not started
Week 3 | Jun 15–21 | Log every run: change, score, delta vs baseline, keep/drop, why | Both | Infra | Not started
GATE 3 | Jun 21 | TRAJECTORY TEST: own changes beat baseline above noise AND idea queue is LONGER than at week start. Slope matters more than absolute score. | Both | Gate
Week 4 | Jun 22–30 | Consolidate gains on the best-performing direction | A | Method | Not started
Week 4 | Jun 22–30 | Harden the submission; re-verify compute envelope | B | Infra | Not started
Week 4 | Jun 22–30 | Write the month up in the results log (seeds the paper either way) | Both | Study | Not started
Week 4 | Jun 22–30 | (Optional insurance) Get one AGI-3 preview game responding to a scripted agent — ~2-3 hrs | B | Setup | Not started
FINAL GATE | Jun 30 | Run the go/no-go on the Gates tab. 3–4 green = continue AGI-2. Reproduced-but-stuck + empty idea queue = switch to AGI-3 (pipeline/harness/log all carry over). | Both | Gate
| Tasks done: | 0 / 19 (incl. gates)

## Gates
Go / No-Go Gates
Tick each criterion. The weekly gates keep you honest; the Final Gate decides AGI-2 vs switch to AGI-3.
When | Gate / Criterion | Met? | Notes
Gate 1 — Jun 7 | Baseline reproduced on Kaggle within tolerance
Gate 1 — Jun 7 | Local eval harness produces the same numbers as Kaggle
Gate 2 — Jun 14 | A scored submission has landed on the leaderboard
Gate 2 — Jun 14 | Submission runs comfortably inside the 12h / 1-GPU budget
Gate 2 — Jun 14 | Error analysis gives a ranked list of failure clusters
Gate 3 — Jun 21 | Our own changes beat the baseline by a margin above noise
Gate 3 — Jun 21 | Untried-idea queue is LONGER than at the start of the week
FINAL — Jun 30 | Baseline reproduced offline (table stakes)
FINAL — Jun 30 | Own changes beat baseline by a meaningful margin
FINAL — Jun 30 | Non-empty queue of promising ideas
FINAL — Jun 30 | Team is energized, not grinding
DECISION | Rule of thumb at Jun 30:
3–4 of the FINAL criteria = Yes → Continue AGI-2; you're on a real slope.
Reproduced but stuck at baseline + empty idea queue → Switch to AGI-3.
Couldn't even reproduce the baseline offline → Fit/infra problem; lean toward switching.
Switching is not a loss: Kaggle pipeline, eval harness, team workflow, and the results log all carry over to AGI-3.

## Results Log
Results Log
Log every experiment from day one. This is your debugging trail AND the skeleton of the paper. Keep the discipline even when busy.
Date | Who | Change / experiment | Baseline score | New score | Delta | Keep? | Why / next idea
2026-06-05 | A | Forked TRM baseline, reproduced public-eval | 0% | 7.2% | 7.2% | Keep | Matches reported ~7%. Baseline established.

## Setup & Constraints
Setup & Hardware Constraints
Read once, pin forever. Design every method to fit the eval envelope from day one.
Item | Detail
Eval envelope (HARD) | Final scored submission runs offline in a Kaggle notebook on a single GPU (historically P100-class) for up to 12 hours, no internet. Confirm the exact 2026 spec on the Kaggle page. Every method must fit THIS.
Scoring | Submit exactly 2 predictions per test input; if either exactly matches ground truth, that task scores 1, else 0. Final = average. Exploit the 2 attempts.
Mac mini 64GB (role) | Development cockpit, NOT the training box. Use for: eval harness, augmentation/data pipeline, results log, light local inference (MLX or llama.cpp, quantized models fit easily in 64GB).
Mac — do NOT | Don't try to run the CUDA TTT stack (unsloth, vLLM, bitsandbytes 4-bit, flash-attention) on Metal. It's a time sink — they're CUDA-only or poorly supported on MPS.
Mac — happy exception | TRM (~7M params) is small enough to actually TRAIN locally via MLX or PyTorch-MPS. Good fit for your hardware and a strong-eng / lighter-ML team.
Dev-time training | Use Kaggle's free GPU notebooks (separate from the submission) or a cheap rented GPU (Colab / RunPod / Lambda). Keep versions pinned so 'works on my Mac' == 'works in eval'.
Storage (2TB) | Non-issue. ARC data is tiny and checkpoints are small. Plenty of headroom.
Method steer | Hardware + 12h/1-GPU envelope both point to the lean end: TRM-style or a single small-model TTT, not a big multi-GPU ensemble you couldn't submit anyway.
Open-source rule | Prize eligibility requires open-sourcing your solution BEFORE receiving official private scores. Use a permissive license (CC0 or MIT-0). Keep repo hygiene from day one.
Baselines to fork | NVARC (2025 1st, TTT+TRM), MindsAI (2025 3rd, engineered TTT) — both open-source with papers. TRM (2025 paper winner) — smallest and most tractable to modify.